## Slide 1
Strategic Enrollment and Student Success Plan
transition REPORT
July, 2020

## Slide 2: contents
1 | SESS PLAN: OVERVIEW AND STRUCTURE
2 | SESS SUMMARY OF WORK
3 | OBJECTIVE SUMMARY
4 | NEXT STEPS AND RESOURCES

## Slide 3: SESS Plan Overview and Structure
1

## Slide 4: SESS Implementation an integrated approach to implementation
The Strategic Enrollment and Student Success Implementation Team reinforced that enrollment and student success is “everyone’s business” by managing the integrated execution of UNC’s SESS Plan.
SESS Project Management
Strategic Priorities
Priority #1 Action Team
Priority #2 Action Team
Priority #3 Action Team
Priority #4 Action Team
  Vision
Strategic Enrollment and Student Success Implementation Team
Key Enablers
Marketing & Comms
Data, Tech & Systems
Financial Sustainability
SESS Implementation Leadership Team
The Implementation Leadership Team (ILT) provided oversight and decision-making authority on proposals
The Implementation Team met monthly to be made aware of, vet, and collectively provide input on initiatives related to the strategic priorities for undergraduate enrollment and student success that should be sent up to the ILT for approval.
The Action Teams will be co-chaired by IT members and are where the work gets done. Co-chairs bring proposals and progress back to the IT monthly.

## Slide 5: implementation team SESS Plan implementation team members
Joan Clinefelter, Professor of History (Co-Chair)
Michelle Quinn, SVP and CFO
Katrina Rodriguez, VP of Student Affairs
Mark Anderson, Provost
Allie Steg-Haskett, VP of Advancement
Olga Baron, Executive Director of Center for International Education
Kim Black, Director of Assessment
Eryka Charley, Director of Native American Student Services
Burkhard Englert, Dean, College of Natural & Health Sciences
Kiki Gilderhus, Interim Dean, College of Performing & Visual Arts
Matt Goetzel, Director of Institutional Reporting and Analysis Services
Randy Larkins, Assistant Professor of Applied Statistics and Research Methods
Chris Marston, Associate Dean, College of Humanities & Social Sciences
Malaika Michel-Fuller, Student Trustee
Marty Somero, Director of Financial Aid
Stephanie Torrez, Assistant Vice President for Student Success
Gardiner Tucker, Dean of Students
Jenna Finley, Exec. Dir. Student Affairs
Charlie Couch, Registrar
Lyndsey Crum, AVP of Alumni Relations
Cris de la Torre, Professor of Finance
Melissa Henry, Professor & Assistant Director of Undergraduate Nursing Programs
Aldo Romero, Cumbres Director
Phil Wyperd, IT Director
Chris Bowers, Project Manager
Implementation Leadership Team (ILT)
Implementation Team (IT)
Project Management

## Slide 6: ACTION teaM SESS Plan ACTION team members
ACTION TEAM 1
Lyndsey Crum, AVP Alumni Relations
Kiki Gilderhus, Interim Dean PVA
Whitney Bonner, Ass. Dir. Recruitment & Outreach
Erin Datteri-Saboski, Ass. Dir. New Student Experience
Selene Ortiz, Student Senate
Adrina Pawlak, Coordinator of Outreach, Financial Aid
Nathan Raugutt, Academic Advisor
Aldo Romero, Dir. Cumbres
Justin Van Nostrand, Digital Marketing Specialist
Rudy Vargas, Coord. Of DREAMer Engagement
Renee Welch, Dir., Center for Career Readiness
ACTION TEAM 2
Charlie Couch, University Registrar
Sarah Goodrum, Professor
Dawit Senbet, Professor
Beckie Croissant, Director NHS Advising Center
Darren Ilett, Assistant Professor
Jennifer Major, Assistant Director Financial Aid
Pepper Mueller, Instructor & Advisor
Nancy Karlin, Professor
Olga Baron, Exec. Dir., Center for International Education

## Slide 7: ACTION teaM SESS Plan ACTION team members
ACTION TEAM 4
Stephanie Torrez, AVP for Student Success
Melissa Henry, Professor
Eric Peterson, Professor
Cris de la Torre, Professor
Marion Deutsch, Advising and Retention Specialist
Seferino Gurule, Student Development Specialist
Melissa Hoffner, Dir. of Tutorial Services
Chris Freeman, Dir. of Soar
Sherri Frye, Early Alert & Project Manager
Patricia Escobar, Dir. Cesar Chavez Cultural Center
Kim Black, Dir. Of Assessment
ACTION TEAM 3
Jenna Finley, Exec. Dir. Of Campus Community & Climate
Chris Marston, HSS Associate Dean
Montez Butts, Dir. Of Residential Education
Marty Somero, Dir. Of Financial Aid
Rosa Law, Dir., MCB Student Advising
Tara Wood, Writing Program Administrator
Annie Epperson, Professor
Nick Hoyle, Ass. Dir. Of Business Analysis
Katelyn Mansker, Ass. Dir. Of Apartment Life
Chris Cobb, Dir. Campus Recreation
Allison Grant, Assessment Data Analyst
Kara LaSota, Dir. Internationll Student and Scholar Services

## Slide 8: SESS SUMMARY OF WORK
2

## Slide 9
Over the last year these action teams have been hard at work implementing over 80 objectives identified in the Strategic Enrollment and Student Success plan.
Many of the objectives were identified by task force work in 2018 but the university had never attempted a wide sweeping implementation across units before.
Trust was built across campus to overcome ingrained thinking around doing “business as usual” all while breaking down our siloed work structure.
Through this process it became clear that the University was already doing great work across campus and there would be no easy solutions.
Several key achievements are listed on the following slides and should be celebrated. The real success of these action teams has been in cross campus collaboration and the structures that have been built to foster a more unified campus in the future.
SESS SUMMARY OF WORK notable achievements

## Slide 10: SESS SUMMARY OF WORK action TEAM notable achievements
ACTION TEAM #1
Formalized the relationship between colleges and admissions through college reps. The Administrative Service Centers (ASCs) will improve this relationship and continue to support the relationship between colleges and recruitment.
Centralized Enrollment activities into one office to increase efficiencies and strengthen coordination within the unit.
Performed a detailed review of communication to prospective students and recommended the formation of the Integrated Communication Council.
ACTION TEAM #2
Through an audit of the process for transfer student applicants AT2 identified credit evaluation as a major bottle neck and worked with the provost office to centralize credit evaluation and cut the time from weeks to days.
Created a Transfer Center landing page to support prospective students
Working to develop clear pathways for each program on campus as it relates to each CC in Colorado.

## Slide 11: SESS SUMMARY OF WORK action TEAM notable achievements
ACTION TEAM #3
Oversaw the creation of the Integrated Network Committee.
Performed comprehensive audit of policies and procedures that inadvertently impede student progression
  Reviewed hold policies in effort of allowing more students to register
  Improved communications of holds to better support students
  Improved student communications so they are easier to understand and actionable
Oversaw the creation of the CRM search committee
Working on standardizing advising practices regardless of college enrolled

## Slide 12: SESS SUMMARY OF WORK action TEAM notable achievements
ACTION TEAM #4
Supported the refinement of the Bear’s First curriculum in Soar and the pilot of delegated support in MCB and NHS.
Evaluated and recommended changes to the seeking nursing and seeking business degree pathways to become compliant with Federal Aid guidelines and better support student success in these programs.
Evaluated and made recommendations regarding university 101
Provided a teacher’s toolkit to support faculty in their efforts to become more student centered and increase retention
  Leading to a new annual practice of the Provost Office promoting the toolkit at the start of each new academic term.
Piloted and studied early performance feedback using low-stakes assessments in ENG122
Delegated support for Bear’s first and the EPF in ENG122 ended up not being as effective as hoped and will not continue but great work has been achieved attempting new techniques and using lessons learned to become better every year.
  Leading to important program enhancements in the Bears First curriculum which will be launched in fall of 2020.

## Slide 13: OBJECTIVE SUMMARIES AND OWNER GOING FORWARD
2

## Slide 14: OBJECTIVE SUMMARY priority 1: FTFT Admissions & Enrollment – initiatives
Initiative 1: Establish a formalized partnership between Admissions, Colleges, and campus-wide units that enhances the recruitment and yield of prospective students.
 | Objective | Outcome | Owner | Document Link
1.1 | Designate Admission Rep(s) for each College; define roles and develop incentives for faculty service engagement. | Representatives have been assigned for each college. | Admissions | Admissions Rep Roles (approved Aug 2019)
1.2 | Increase involvement and coordination of current undergrad students, faculty, and staff in recruitment & yield events (ex. Expand Ambassador program to off-campus events, provide point of contact in each academic unit to coordinate with admissions). | Central reorganization of recruitment and orientation events into the New Student Experience team, working in partnership with College Admissions reps, provides the structure to expand faculty, staff & student involvement. | Admissions, Colleges, Current Students | Proposed approach to events Support for non-recruitment events
1.3 | Communicate career pathways and outcomes for academic programs in marketing and communications materials. | 1.3,1.4, and 1.5 are addressed by an integrated advancement team working with communication specialists in the ASCs and the program directors, deans, and alumni to understand our data and communicating it. The structural changes that have been implemented create a holistic, non-siloed approach that will allow UNC to understand and communicate our career outcomes like never before. 1.3 Advancement produced alumni employment dashboards for use in marketing and communication of career pathways and outcomes 1.5 Conducted initial inventory with self-identified information Summer 2019. Next Steps: Use college admissions reps to facilitate annual updates. | Marketing | Alumni Employment Outcome Dashboard
1.4 | Expand partnerships with Career Services and Development & Alumni Relations to incorporate alumni in recruitment and yield events and communications. |  | Admissions Career Readiness Alumni Relations | Alumni-Admissions Partnerships
1.5 | Work with colleges and their departments to inventory and/or establish program differentiators (both experiential and outcomes) to promote in respective student markets. |  | Marketing & Admissions | Benefits & Features (2019)
1.6 | Ensure market demand information is used in the new program proposal process to determine alignment with UNC’s strategic plan and resource investments. |  |  | 

## Slide 15: OBJECTIVE SUMMARY priority 1: FTFT Admissions & Enrollment – initiatives
Initiative 2: Shift Admissions staff and approach to enhance intentional and relational recruitment efforts.
 | Objective | Outcome | Owner | Document Link
2.1 | Develop actionable recruitment targets for Admissions Counselors (AC’s) by territory / target audiences; aligned with UNC’s vision and academic capacity. | Recruitment targets will be established annually and adjusted as market conditions change | Admission | 
2.2 | Determine appropriate structure for admissions such that it enables a relational approach and increases focus / expertise on WUE and other in- and out-of-state markets.1 | A centralized admissions structure was implemented to bring all recruitment activities into the office of Enrollment | Enrollment Management | SESS-AT1-Admissions-Review
2.3 | Develop UNC’s prospect development campaign and name-buying strategy; focus on academic areas of interest and partner with Colleges. | Admissions, working with college representatives, will identify opportunities for growth and develop appropriate and targeted recruitment campaigns | Admissions | 
2.4 | Centralize all re-entry processes within Admissions; align standards & partnerships with academic probation, Registrar, etc. |  | Admissions | 
2.5 | Increase partnerships with high schools in Northern Colorado; collaborate with faculty to get inside classrooms at local high schools. | Work is needed to collaborate with dual enrollment, currently under the office of extended campus. Once responsibilities are clarified Enrollment and marketing can support these programs as needed. | TBD | 

## Slide 16: OBJECTIVE SUMMARY priority 1: FTFT Admissions & Enrollment – initiatives
Initiative 3: Further integrate marketing and communications to achieve a unified approach across admissions-related communications, focused on UNC’s value proposition and differentiators.
 | Objective | Outcome | Owner | Document Link
3.1 | Expand existing integrated marketing and communications efforts to bring together stakeholders across campus to formalize partnerships & continue work on a structured, integrated, marketing and communications plan for student outreach and engagement. | Recommendation to establish an Integrated Communication Committee responsible for the collaborative development of an integrated marketing plan. | Integrated Communication Committee | Integrated Communication Retreat Summary and Recommendations
3.2 | Develop an internal comms network to inform campus stakeholders of upcoming communications, marketing messages, and events to support more collaborative efforts and strategic knowledge-sharing. |  | Integrated Communication Committee | 
3.3 | Ensure marketing and communications are aligned across all UNC technology and media platforms (ex. Website, mailers, emails, social media, etc.). |  | Marketing | 
3.4 | Develop differentiated, market-specific value propositions for target recruitment markets​; focus on geographic and demographic qualities to enhance experience customization. | The integrated communication committee should consider developing marketing personas to address this objective | Marketing | 
3.5 | Design dedicated marketing campaigns and intentional messaging to focus on career outcomes, teacher/scholar model, coaching support, scholarships, and overall value of a UNC degree. | This will be the outcome of Marketing working with the Integrated Communication Committee | Marketing | 
3.6 | Work with colleges and their departments to inventory and/or establish program differentiators (both experiential and outcomes) to promote in respective student markets. | Admissions continues to work with college reps to gather program benefits and differentiators. This data needs to be shared with Marketing to provide content. | Admissions/ Marketing | Features & Benefits (2019)

## Slide 17: OBJECTIVE SUMMARY priority 1: FTFT Admissions & Enrollment – initiatives
Initiative 4: Enhance onboarding strategy to be a seamless experience for incoming students, beginning at acceptance through first Fall semester.
 | Objective | Outcome | Owner | Document Link
4.1 | Enhance integrated onboarding curriculum that incorporates Admissions Counselors into Orientation and Welcome Events in Fall & Spring semesters. | The Enrollment unit has been restructured and the work of extended onboarding in this capacity will be considered by New Student Experience | New Student Experience | Proposed FY21 Structure
4.2 | Enhance role of student ambassadors beyond Campus Visits to become integrated in onboarding efforts beginning May 1. | This is complete based on the combination of New Student Orientation into Admissions. | New Student Experience | 
4.3 | Expand Spanish-speaking services during orientation events for all; additionally, increase parent orientation offerings for first-generation students. | New Student Experience is working with development to expand Spanish-speaking services. Budget was allocated for FY21 before budget cuts. | New Student Experience | 
4.4 | Identify academic advisors earlier in the matriculation process (post May 1) and assign one point of contact to admitted students. | See Priority 3, objective 2.1 & 2.4 |  | 
4.5 | Extend onboarding process into first six weeks of Fall semester by expanding existing curriculum and partnerships in support of student success. | New Student Experience will work with Student Affairs to determine the best comprehensive solutions for onboarding new students | Student Affairs/ New Student Experience | 
4.6 | Develop, manage and execute a coordinated communication plan to minimize summer melt. | Iterative process for each unique recruitment cycle. Admissions will continue to develop coordinated plans and build on success year over year. | Admissions | 2019 Summer Schedule

## Slide 18: OBJECTIVE SUMMARY priority 2: Transfer Enrollment – initiatives
Initiative 1: Grow UNC’s transfer recruitment pipeline by enhancing presence and relationships at local community colleges and developing formalized transition partnerships.
 | Objective | Outcome | Owner | Document Link
1.1 | Create an integrated group of individuals to guide management of finalizing formal transition partnership with Aims, and then mirror that partnership with Front Range. | Aims2UNC has become well established and is generating a robust pipeline of transfer students. | Academic Affairs | Aims2UNC
1.2 | Reallocate or consider investing in dedicated Transfer Admission Counselor(s) focused on transfer territories, building partnerships, and streamlining yield and onboarding policies / procedures.1,2 | Dedicated transfer counselors was part of the Enrollment restructuring and needs increase budget to finalize | Admissions | SESS-AT1-Admissions-Review
1.3 | Develop TR-specific communications plan (academic pathway focused) in Slate to enhance recruitment and yield efforts. | This will be the outcome of Marketing working with the Integrated Communication Committee | Marketing | 
1.4 | Establish regular touchpoints with prospective Transfer students on Community College campuses (ex. Advising Days). | This was being developed with the dedicated transfer counselors but now needs to be rethought in light of COVID. Lessons learned could be built upon to be more efficient in outreach. | Admissions | 
1.5 | Enhance training for admissions counselor(s) focused on TR recruitment; partner with Registrar and Colleges to ensure admission counselors are current and accurate in their knowledge of course equivalency information. | Expectations have been set and Admissions is working with individual units to enhance counselor preparations | Admissions | 
1.6 | Develop strategy for students who left UNC previously with information on how to transfer in / re-enroll in the university. | With restructuring and new leadership this objective should be considered as the Integrated Communication Committee considers target demographics | Admissions/ Marketing | 

## Slide 19: OBJECTIVE SUMMARY priority 2: Transfer Enrollment – initiatives
Initiative 2: Enhance support services and resources for transfer students beginning at pre-enrollment through graduation.
 | Objective | Outcome | Owner | Document Link
2.1 | Add admissions checklist item for all admitted transfer students to submit current term transcript if currently enrolled at another college and expedite review at UNC. | Transfer evaluations have been expedited by reviewing most courses in the registrar's office. Admissions is looking for ways to operationalize reminding students | Admissions/ Registrars | 
2.2 | Establish foundation for transfer student services by designating 1-2 staff members within Admissions to lead transfer recruitment, yield, onboarding, and success efforts. | Dedicated transfer counselors was part of the Enrollment restructuring and needs increase budget to finalize | Enrollment | SESS-AT1-Admissions-Review
2.3 | Partner with current UNC transfer students to develop transfer student ambassador program to provide mentorship during pre-enrollment through first term. | Under the new admissions structure consider this being the responsibility of NSE | Enrollment | 
2.4 | Consider expanding existing transfer resources (Reisher, Veterans Services, etc.) to offer additional resources & support for all transfer students. | Resources cannot be decoupled from these units, but these programs can serve as best practices for supporting transfers | Enrollment/ Academic & Student Affairs | 
2.5 | Consider and evaluate need to create a Center for Transfer Student Support (CTSS). | Initial step will be a virtual Transfer Student Support page. In the future, a physical space may be possible | Enrollment | Virtual Tranfer Center
2.6 | Develop early onboarding programming for transfer students during evenings/weekends in the summer (Ex. Include active learning initiatives tied to academic paths). | New Student Experience will continue to deliver content in an accessible way to new students | New Student Experience | 
2.7 | Conduct a study on who our transfer students are (demographics, academic paths, backgrounds, parents, etc.) | Enrollment will continue to develop their understanding of both current and target demographics | Enrollment | 

## Slide 20: OBJECTIVE SUMMARY priority 2: Transfer Enrollment – initiatives
Initiative 3: Streamline credit evaluation processes and build clear academic pathways to simplify transfer students’ transition to UNC and enhance overall success.
 | Objective | Outcome | Owner | Document Link
3.1 | Create marketing & recruitment plan for high school students participating in dual enrollment courses. | This will be the outcome of Marketing working with the Integrated Communication Committee | Enrollment/ Marketing | 
3.2 | Appoint college-based representatives to manage program-specific credit evaluation processes; establish clear policies for timely evaluation. | Revised transfer evaluation process address this and expedites review | Registrar | 
3.3 | Require that academic programs / departments establish articulation agreements with local community colleges, coordinated by a representative in each college | Transfer guides for each program and Colorado Community College will be done by fall 2020 | Registrar | Transfer Guide
3.4 | Develop clear academic pathways for high demand transfer programs and publish to be easily accessible online. |  |  | 
3.5 | Empower AP for Undergraduate Studies to set deadlines and enforce policies related to transfer student credit evaluation processes. | Revised transfer evaluation process address this and expedites review | Registrar | 
3.6 | Evaluate and simplify LAC requirements for transfer students. | Faculty senate approved simplified LAC requirements. Implemented Fall 2021 | Academic Affairs | 
3.7 | Registrar and Colleges should collaborate to explore student-centered course scheduling recommendations that create flexibility with additional evening / online course offerings, and include course sequencing, scheduling, and course management. | Continual evaluation of student demographics and appropriate course scheduling | Academic Affairs | 

## Slide 21: OBJECTIVE SUMMARY priority 3: student success – initiatives
Initiative 1: Define membership of the integrated network and create a standing committee to manage the network’s activities going forward.1
 | Objective | Outcome | Owner | Document Link
1.1 | Appoint co-leads of the standing committee to manage the creation of the network. | The Integrated Network Council (INC) is being led by Stephanie Torrez (SOAR) and Tuck Tucker, Dean of Students. | INC | 
1.2 | Create the standing committee that is comprised of faculty, advisors, Student Affairs units, Bear Central, Admissions, Assessment and Student Academic Success to learn from students and identify their highest-priority needs that should be addressed by the network. | INC membership has been determined and members invited by the INC chairs, Stephanie Torrez and Tuck Tucker. | INC | 
1.3 | Establish standards of practice, training, and clear roles and responsibilities for each member / node of the network. | INC charter outlines initial processes; INC has a plan for summer 2020 and will continue this work in the fall of 2020. | INC | INC Charter
1.4 | Establish a schedule and strategy for the Standing Committee / Action Team to come together for case management meetings, building from SA model today. | INC will take over these duties, but a case management model has been determined to be of little use. | INC | 
1.5 | Establish and implement norms for engaging with students as their needs are identified and they are referred and directed through the network, focusing on a developmental/coaching mindset. | INC will develop this as they begin their work in summer and fall of 2020 | INC | 
1.6 | Audit other existing student success-related efforts to identify additional sources of capacity that could be integrated / combined. | INC will take on these duties | INC | 

## Slide 22: OBJECTIVE SUMMARY priority 3: student success – initiatives
Initiative 2: Establish clear standards of practice for advising regardless of College enrolled, shifting the approach to a coaching relationship.1
 | Objective | Outcome | Owner | Document Link
2.1 | Ensure every incoming student is assigned to an advisor prior to registration for first term and hand-off is made by Admissions/Orientation. | Completed. The deans, working with their professional advisors and academic departments ensure incoming students are assigned advisors. | Admissions, Orientation, Deans | See reports under 2.4 below
2.2 | Establish updated expectations and incentives for faculty serving in advising roles. | Advising Toolkit in progress | Deans and chairs/dirs | Improving faculty advising
2.3 | Build on existing work started by SAS to develop training and professional development aligned to updated advising approach / standards of practice. | CETL offered workshops in AY 2019/20 and will continue to do so in the future. INC will also likely address this concern. | CETL, INC | CETL update and info sheet; Faculty Devel and CETL Matrix
2.4 | Implement full-time College-based advisors to support students during their first two years.3 | Completed; all colleges have professional advisors; HSS faculty will continue to advise their majors but understand and use the professional advisors for coaching outreach. | Deans | List of Professional Advisors by Program Slate ready Academic Contact List
2.5 | Streamline process for advisors to engage with the integrated success network, creating mechanisms for inputting information for others and reviewing information shared by others. | On hold due to CRM delay, however Degree Works continues to be updated with templates from programs to guide students and advisors on the major requirements. | INC, IT (for the Degree Works update) | 
2.6 | Develop efforts / communication plan directed at continuing students to encourage registration by term to ensure students return to UNC to complete degree. | Team worked with Colleges to get departments/advisors to do outreach in AY2019/20. Will continue in next AY. | Deans, advisors, depts/ programs | Academic Contact Timeline with sample MCB Communication

## Slide 23
 | Objective | Outcome | Owner | Document Link
3.1 | Connect Admissions, Orientation, Student Affairs, Student Academic Success and College representatives to build a sequenced and integrated onboarding approach from confirmation through first few weeks of fall semester. | Due to the Covid outbreak, Student Affairs and Academic Affairs special committees are developing fall 2020 onboarding; onboarding for fall 2021 work will begin in fall. | Admissions, Orientation, SAS | 
3.2 | Continue to work on faculty standards of practice around gateway course instruction and early alert strategies. | Team 3/4 completed a study of problematic course combinations, which will be given to deans at their SESS orientation. Reports completed on faculty instruction and LAC. Work will continue within Colleges/programs; Mini toolkit distributed summer 2019; updated kit will be distributed summer 2020 | Deans and programs | Teaching Toolkit; Faculty Mini Toolbox 2019 See also reports under 3.3 and Early Performance report under team 4, GET LOCATION
Initiative 3: Develop an onboarding and first term experience and set of resources to ensure students acclimate to UNC.1
OBJECTIVE SUMMARY priority 3: student success – initiatives

## Slide 24
Initiative 3: Develop an onboarding and first term experience and set of resources to ensure students acclimate to UNC.1
 | Objective | Outcome | Owner | Document Link
3.3 | Evaluate degree pathways and recommended first-term course plans to alleviate risky course combinations and increase likelihood of first-year success. | See the attached reports; Nancy Machette also led a group of chairs with classes that have a high DFW rate and worked with the chairs to develop responses. DFW rates declined in all Colleges except PVA in Fall 2019. See SESS dashboard; info will be updated in fall on the dashboard with Spring 2020 results For reference see original Huron DFW analysis: Huron UNC DFW Analysis | Deans and chairs; Clinefelter will ensure SESS dashboard is updated | Executive Summary Problematic Course Combinations; Problematic Course Combinations; Potential Gateway Courses using 5yr summary DWFI Report with Tutoring offerings NHS Leadership High DFW Report 2019
3.4 | Invest in Degree Works module for flexible degree plans. | Degree Works planner capability should be ready by the fall. Templates for many programs are already completed. Note that advisors need to be informed and trained as needed re the new Degree Works capability. | Registrar | 
OBJECTIVE SUMMARY priority 3: student success – initiatives

## Slide 25: OBJECTIVE SUMMARY priority 3: student success – initiatives
Initiative 4: Evaluate and streamline student business services-related policies and procedures – that may inadvertently impede student progression – to be student-centered and welcoming.
 | Objective | Outcome | Owner | Document Link
4.1 | Review current hold policies to identify unintended barriers. | Completed. Audit of holds revealed that most holds are related to financial issues. Financial aid has instituted programs and better communications with students so that they know if they have a hold, why, and how to get the hold removed. | Registrar, Financial aid, internal communications | Holds notifications Holds Preventing Registration
4.2 | Review students with holds and engage with them to take action to alleviate/remove hold and support their efforts to register for Fall classes in April. | Team engaged with Bear Central offices to improve communications with new email language employed to improve student outreach. Work will continue | Bear Central, internal Comms | See host of comms info under SESS, Action Team 3, files, Folder Communications (FARB)

## Slide 26: OBJECTIVE SUMMARY priority 3: student success – initiatives
Initiative 4: Evaluate and streamline student business services-related policies and procedures – that may inadvertently impede student progression – to be student-centered and welcoming.
 | Objective | Outcome | Owner | Document Link
4.3 | Review relevant recent student survey results and execute student focus groups and a potential survey to identify highest priority barriers students face. | Analysis completed, with recommendations. Mental health, student readiness and financial issues top the list. See also Team 3, folder Survey Data for more | Admissions, Financial Aid, Student Affairs | Student Barriers Data and Recs Stayers and leavers Report Executive Summary
4.4 | Create a financial literacy program for students. | BAFN 240 Intro to Personal Financial Planning already exists and is an option in the current LAC. Revisit for the new LAC. | MCB | 
4.5 | Continue focus on Bear Central integration and focus added customer service capacity on supporting students through verification and financial issues. | Reorganization especially in Admissions completed. Bear Central continuing to improve communications with students so they can better serve them. | Bear Central | See host of comms info under SESS, Action Team 3, files, Folder Communications (FARB)
4.6 | Conduct a study on A/R holds for better understanding of student experience and ramp up earlier engagement to assist students. | The primary finding was that while the holds are numerous, most are valid. Better communication with students has begun and is ongoing. | Registrar | Audit Holds Preventing Registration

## Slide 27: OBJECTIVE SUMMARY priority 3: student success – initiatives
Initiative 5: Enhance utilization and integration of current technologies and CRM tools on-campus to support student success network.
 | Objective | Outcome | Owner | Document Link
5.1 | Develop the appropriate roles and responsibilities for each stakeholder group that will require use of Student Success Collaborative. | When it is ready, INC will take this on. | INC | 
5.2 | Inventory/review the tools used to track "student profile-related" information and develop a data/technology infrastructure that allows for information-sharing throughout the integrated student success network. (Student Success Collaborative, Maxient, EMMA, etc.) | CRM committee evaluated a new CRM which is on hold due to the Covid virus. Will reevaluate the committee's findings in fall 2020. | Provost INC? | 
5.3 | Consider TF recommendation to create an Office of Institutional Effectiveness to serve as data governance and integration leader, conduct ongoing and proactive student success-related analytics, and deliver data insights to stakeholders. | Completed. The new office has been created, under direction of Office of Finance. SESS dashboard provides detailed analytics that will be reported out to campus. | Office of IE | 

## Slide 28: OBJECTIVE SUMMARY priority 4: targeted coaching – initiatives
Initiative 1: Establish a scaffolded approach from point of admission through the first term for students who meet the criteria for targeted and proactive coaching and development.
 | Objective | Outcome | Owner | Document Link
1.1 | Confirm criteria for who will be eligible for targeted and proactive coaching, and develop communications that excite students about participation. | Completed. Working with Admissions, Soar provided proactive coaching to all students with less than a 3.0 GPA and on academic probation coaching in fall 2019; this Bears First program will continue in the fall 2020. | Admissions SOAR/Bears First | Bears First Admitted with support – detailed List of Implemented Interventions and Strategies 2019/20
1.2 | Evaluate pre-registration option, current versus prospective student model and timelines. | Evaluation completed ; Committee found no benefit in terms of student commitment or in reducing summer melt; recommended to not implement. |  | Pre-Registration Committee Report
1.3 | Identify cohort of advisors to provide designated support to students and connect students to them early to provide advanced advising prior to first term registration. | The Bears First program connects students with advisors. | Soar, Bears First | 
1.4 | Develop curriculum of pre-enrollment activities to complete, with regular touchpoints and monitoring from UNC (i.e. Khan Academy). | Working with Orientation, the Action Team found that this would be of limited benefit and decided not to implement at this time. |  | 
1.5 | Extend the existing peer mentorship model for incoming students during orientation such that peer mentorship continues formally through the first term (and beyond if desired). | Work is ongoing and being adjusted due to the Covid virus. Students in the fall will be placed into cohort groups with RAs providing programming. A peer mentoring survey was sent out and collected data on existing peer mentoring programs. The raw data from that survey was shared with AT 3. | Admissions, Orientation, Student Affairs/RAs/Onboarding Task Forces | Survey Questions on Peer Mentoring programs at UNC
1.6 | Consider a longer-term set of cohort-based orientation experiences specific to target populations. | Bears First will evaluate in future. | Soar/Bears First, perhaps INC | 

## Slide 29: OBJECTIVE SUMMARY priority 4: targeted coaching – initiatives
Initiative 2: Move forward with the proposal to reconfigure the MEAP Office to provide academic success coaching and proactive advising focused on the population of students that are most at risk for academic difficulty or attrition.2
 | Objective | Outcome | Owner | Document Link
2.1 | Establish clear partnership and roles/responsibilities between this new office and key collaborators (Colleges, Admissions, Orientation, Financial Aid, Registrar), and ensure adequate access to SSC data and information to guide decision-making. | Completed with the creation of Soar in summer 2019. | Soar | 
2.2 | Establish clear partnership and roles/responsibilities between this new office and key Student Affairs collaborators (Student Affairs, Res Life, etc.). | Completed with creation of Soar and INC | Soar/INC | 

## Slide 30: OBJECTIVE SUMMARY priority 4: targeted coaching – initiatives
Initiative 3: Determine necessary adjustments to “Seeking Nursing” and “Seeking Business” degree pathways to enhance student success.1
 | Objective | Outcome | Owner | Document Link
3.1 | Collectively align on how to handle recent changes in financial aid regulations that may impact UNC's ability to offer "seeking" designations. | Completed. Seeking designation no longer exists. Exploring Nursing students who are not admitted into the program at end of 30 credits will have do declare another major; Business students not accepted into the program upon admission will have to declare a different major and reapply later. | Admissions Nursing MCB | 
3.2 | Evaluate current policies and constraints associated with the "Seeking Business" track to determine if the current cap on enrollment into MCB is appropriate. | Seeking business no longer exists as a designation. |  | 
3.3 | Determine if a "General Business" track for incoming students could be an alternative to "Seeking Business." | Seeking Business no long exists. Students who do not meet admissions requirements must select another major until they meet the requirements. | Registrar/MCB | 

## Slide 31: OBJECTIVE SUMMARY priority 4: targeted coaching – initiatives
Initiative 3: Determine necessary adjustments to “Seeking Nursing” and “Seeking Business” degree pathways to enhance student success.1
 | Objective | Outcome | Owner | Document Link
3.4 | Develop coordinated and specific coaching and advising services for "Seeking Nursing" and "Seeking Business" students starting with orientation, and ensure all students are connected to an advisor prior to orientation. | Both programs offered advising programming for incoming students in Fall 2019; analysis of those programs is ongoing and being adjusted as needed. | MCB, Nursing | Bears First Admitted with support – detailed
3.5 | Utilize College Advising Teams to monitor performance of "Seeking Nursing" and "Seeking Business" students to proactively reach out to those that struggle in their first term to provide coaching. | Nursing and Business both offered advising/programming adapted to fit the needs of students and the capacity of the college/program for AY2019/20. Will continue into future | MCB, Nursing | Bears First SESS Evaluation Final Report
3.6 | Consider developing additional / alternative health-related pathways for students who do not make it into the Nursing program. | Nursing developed an alternative health major; major is being worked on by program/provost. Nursing has also revamped application process. | Nursing/ Provost | Nursing Four year Plan

## Slide 32: OBJECTIVE SUMMARY priority 4: targeted coaching – initiatives
Initiative 4: Evaluate and update degree planning and coaching pathways that will benefit the target population.1,2
 | Objective | Outcome | Owner | Document Link
4.1 | Explore first- and second-year course combinations in key degree programs that negatively impact student progression. | Completed. Report information needs to be shared with deans, chairs for programs to take the next steps. Infor will be shared at Deans orientation. See the Huron DFW report here for context: UNC DFW Report Huron | SESS fall 2020; Deans and chairs | Executive Summary Problematic Course Combinations; Problematic Course Combinations; Potential Gateway Courses using 5 YR summary DFWI Report with tutoring offerings
4.2 | Determine updated approach to University 101 in light of recent changes to how it is recognized within the LAC and need for (a) academic skill development and (b) acclimating to university setting/culture. | UNIV 101 will continue to be recommended by programs/orientation. See overview of UNIV 101 and outcomes in report. |  | UNIV 101 Report
4.3 | Consider cohort-based course scheduling and advanced first term registration advising for target populations. | Committee determined that this is unworkable at this time. |  | 

## Slide 33: OBJECTIVE SUMMARY priority 4: targeted coaching – initiatives
Initiative 4: Evaluate and update degree planning and coaching pathways that will benefit the target population.1,2
 | Objective | Outcome | Owner | Document Link
4.4 | Establish early alert requirements and low-stakes assessments in core gateway courses with high DFW rates. | Pilot program conducted with 22 ENG 122 courses in fall 2019 completed and evaluated. Findings indicate that the time and effort did not result in meaningful outcomes. Faculty Toolkit distributed in the fall encouraged more classes to include early, low-stakes assignments with the result that all Colleges reduced DFW rates in Fall 2019. Chairs of programs with high DFW rates in gateway courses also met regularly with Nancy Matchett, Interim Associate Provost of Undergraduate Students in AY 2020 to develop responses. DFW rates will continue to be monitored in the SESS dashboard. | Deans and Chairs; results posted on the SESS dashboard | Implemented Interventions and Strategies for Students at Greatest Risk of Attrition; Early Performance Results; EFP Final Report
4.5 | Provide DegreeWorks training to students during orientation and onboarding, and provide training to advisors so they use it as a primary advising tool. | Completed. Orientation introduces students to Degree Works; professional advisors and faculty advisors continually work with students on use of Degree Works in advising sessions. | Orientation; College Advising Centers, faculty advisors | 

## Slide 34: Next steps AND RESOURCES
4

## Slide 35: Next Steps Transition SESS objectives to standing units
Dr. Clinefelter to present SESS work at the Dean's Retreat August 6th & 7th
Meetings with unit leaders as needed to clarify and hand off
Attend each colleges Academic Leadership Meeting to highlight the work of SESS
Schedule a meeting with CETL to handoff the role of sustaining professional development ensuring that work is collaborated with stakeholder across campus.
Schedule to present at Dean's Council after fall mid-terms to emphasize retention

## Slide 36: resources admission and student success dashboards
Admissions Monitoring
Student Success